## Work Items
Resource Name | Project | Module | Task | Working with | Owner | SMT
Anjum, Meraj | AIMS | Web UI | Revamping the existing application based on the Controls Style Guide. | Sarkar, Rimple Saddi, Rajat | Saddi, Rajat | Mohammad, Shaji
Dayalan, Deepak | Internal Audit | Audit 360 | Addressing Feedback in the entire UI | Chatterjee, Rajat Prathaba Reddy, Ashok Kumar | Saddi, Rajat | Mohammad, Shaji
Selvam, Naresh Kumar | Reg. Management | RCM Dashboard | Redesigning the existing dasboard for web. Mocks delivered and awaiting response from the onshore folks. | Udatha, Sukumar Grandhi, Girish Kumar | Manda, Ravi Singh, Satvinder3 | Mohammad, Shaji
Selvam, Naresh Kumar | Reg. Management | Performance Metrics | Dashboard design improvement for the demo. Changed color schemes and addressed feedback. Reviewed the developed UI and suggested improvements. | Perumalswamy, Srinivasan Udatha, Sukumar Grandhi, Girish Kumar | Ali, Mir Singh, Satvinder3 | Mohammad, Shaji
Selvam, Naresh Kumar | Reg. Management | Insight 360 | Dashboard design improvement for the demo. Changed color schemes and addressed feedback. Reviewed the developed UI and suggested improvements. | Perumalswamy, Srinivasan Udatha, Sukumar Grandhi, Girish Kumar | Ali, Mir Singh, Satvinder4 | Mohammad, Shaji
Selvam, Naresh Kumar | iCAPs | Issues and CAPs | Designed 3 different options of the layout in the form of wireframe and delivered to the iCAPs team. They have selected one option and have suggested minor changes. | Aggarwal, Anupam Reshimwale, Vikram | Booranaphonsathit, Suwit | Mohammad, Shaji
Selvam, Naresh Kumar | iCAPs | iCAPs Dashboard | Designing the dashboard showin highlevel information on Issues, Corrective Action plan and Exceptions for different user roles. | Aggarwal, Anupam Reshimwale, Vikram | Booranaphonsathit, Suwit | Mohammad, Shaji
Gunasekaran, Jayaprakash | AML NPA | AML NPA Dashboard | Redesigning the existing dashboard following the style guide and following the new approved blue based color theme. | Kunaparaju, Hari Torlapati, Tatayya | Kunaparaju, Hari | Mohammad, Shaji
Gunasekaran, Jayaprakash | AML NPA | Overview Screen | Redesigning the existing dashboard following the style guide. Also addressing comments/feedback from the onshore team. | Kunaparaju, Hari Torlapati, Tatayya | Kunaparaju, Hari | Mohammad, Shaji
Gunasekaran, Jayaprakash | AML NPA | Product Attribute | Redesigning the existing dashboard following the style guide. Also addressing comments/feedback from the onshore team. | Kunaparaju, Hari Torlapati, Tatayya | Kunaparaju, Hari | Mohammad, Shaji
Karthik Elavazhagan, Praveen | AML NPA | AML Risk Assessment | Converting 3 screens in AML Risk Assessment to HTML and CSS, and parallely working with the dev team. | Grandhi, Girish Kumar Rathinakumar, Mohanram | Ali, Mir Singh, Satvinder3 | Mohammad, Shaji
Karthik Elavazhagan, Praveen | Reg. Management | Performance Metrics | UI improvement for the demo. Changed color schemes and addressed feedback. | Udatha, Sukumar Grandhi, Girish Kumar | Ali, Mir Singh, Satvinder3 | Mohammad, Shaji
Karthik Elavazhagan, Praveen | Reg. Management | Insight 360 | UI improvement for the demo. Changed color schemes and addressed feedback. | Udatha, Sukumar Grandhi, Girish Kumar | Ali, Mir Singh, Satvinder4 | Mohammad, Shaji
Majumder, Sufal | Citi Risk Document Management | Document Management POC | Made HTML CSS updates / changes to the POC UI. Also resolved Jira issues. | Saha, Rishabh Pravinmchandra Rathinakumar, Mohanram | Nallukula, Paul Narayan | Mohammad, Shaji
Majumder, Sufal | Citi Risk Document Management | iDOC Sign Up | Created the initial wireframe and mock up. Also converted it to HTML and CSS. | Agrawal, Akash | Nallukula, Paul Narayan | Mohammad, Shaji
Bharadwaj Gunti, Harish | Internal Audit | Audit 360 | HTML/CSS improvements of the entire UI. | Sahu, Manish | Saddi, Rajat | Mohammad, Shaji
Bharadwaj Gunti, Harish | EWARA | Entire UI | UI enhancements to support screens lesser than 1280px width. UI fixes were done as well. | Kumar, Naresh6 Metha, Kartik | Perumalsamy, Srinivasan Singh, Satvinder3 | Mohammad, Shaji
Bharadwaj Gunti, Harish | eCAMP | Entire Ui | UI enhancements and bug fixes in SIT. | Chauhan, Mayurkumar | Merchant, Siraj Singh, Satvinder3 | Mohammad, Shaji
Titus, Shibu | GRC | PARKM Assessment | New features designing and improvements to the UI | Tarey, Divya Khanna, Sandeep | Shafi, Sufian | Sheeba
Titus, Shibu | GRC | Monitoring Tool Results | UI/UX Designing from the scratch | Tarey, Divya Khanna, Sandeep | Shafi, Sufian | Sheeba
Titus, Shibu | GRC | Taxonomy | UI/UX Designing from the scratch | Tarey, Divya Khanna, Sandeep | Shafi, Sufian | Sheeba
Titus, Shibu | GRC | AU Management | UI/UX Designing from the scratch on top of a select existing features | Tarey, Divya Khanna, Sandeep | Shafi, Sufian | Sheeba
Titus, Shibu | ORMi | Metrics Sollution | complete redesign of the UI. Creating Wireframes. | Tarey, Divya Khanna, Sandeep | Shafi, Sufian | Sheeba
Krishnan D, Hari | ORMi | Metrics Sollution | Understanding the requirement from Shibu and Ideating. | Titus, Shibu | Shafi, Sufian | Sheeba
Kalyanaraman, Gokul | CCB | Continous Monitoring | Created 3 screens for Continous Monitoring. Provided 2 options and have decided on one. | Kokate, Bhupesh | Kokate, Bhupesh | Mohammad, Shaji
Dayalan, Deepak | Citi Insight | Glossary | IE Browser Compatibility improvements | Goyal, Chaitanya | Malla, Chaitanya Raj | Bhowmick, Joy
Mohan, Prakash | Citi Insight | Catelog Management | UI Bug Fixes | Goyal, Chaitanya | Malla, Chaitanya Raj | Bhowmick, Joy
Mohan, Prakash | Citi Insight | LESS POC | Created My Packages screen with Less | Kalyanaraman, Gokul | Malla, Chaitanya Raj | Bhowmick, Joy
S.Ghoshal, Prashant | New Hire
Zuber, Mohammed | Unified Case Manager | Case Manager | UI/UX Design of the 2.8 requirements | Saurab Jaikumar | Patrick, Robbert Bradley, John
Zuber, Mohammed | Unified Case Manager | Work Bench | UI/UX Design of the 2.8 requirements | Himanshu Jaikumar | Boaz Ryan
Chauhan, Ashish Prafulchandra | Unified Case Manager | Total Conduct | Working on responsiveness of the UI to support the minimum resoulution 1440x900 | Saurab Jaikumar | Patrick, Robbert Bradley, John
Chauhan, Ashish Prafulchandra | Unified Case Manager | Work Bench | Working on pattent test screens. Converting the PSDs to HTML and CSS. | Saurab Jaikumar | Patrick, Robbert Bradley, John

## Resource Details
Resource Name | SOEID | Level | Skills | Reorting to | Location | TRS Project ID
Anjum, Meraj | MA27706 | Junior | UI/UX Designer | Vijh, Deepak | Pune
Selvam, Naresh Kumar | NS62530 | Junior | UI/UX Designer | Vijh, Deepak | Chennai | 201807936
Gunasekaran, Jayaprakash | JG62527 | Junior | UI/UX Designer | Vijh, Deepak | Chennai
Karthik Elavazhagan, Praveen | PK14356 | Junior | HTML/CSS Developer | Yarra, Murali Krishna | Chennai
Majumder, Sufal | SM02171 | Junior | HTML/CSS Developer | Yarra, Murali Krishna | Chennai | 201802228
Bharadwaj Gunti, Harish | HB27699 | Junior | HTML/CSS Developer | Vijh, Deepak | Pune | 201813314
Titus, Shibu | ST43410 | Senior | UI/UX Designer | Sabnis, Ajit Anand | Pune
Krishnan D, Hari | HK53794 | Junior | UI/UX Designer | Sabnis, Ajit Anand | Chennai
Kalyanaraman, Gokul | KG18045 | Senior | UI/UX Designer | Sabnis, Ajit Anand | Chennai
Dayalan, Deepak | DD57161 | Junior | HTML/CSS Developer | Sabnis, Ajit Anand | Chennai
Mohan, Prakash | MP36082 | Senior | HTML/CSS Developer | Sabnis, Ajit Anand | Chennai | 201804736
S.Ghoshal, Prashant | PS55308 | Senior | UI/UX Designer | Sabnis, Ajit Anand | Chennai
Zuber, Mohammed | MZ89628 | Junior | UI/UX Designer | Rajbhut, Jaikumar | Pune
Chauhan, Ashish Prafulchandra | AC65099 | Junior | HTML/CSS Developer | Rajbhut, Jaikumar | Pune